## Test Cases
ID | Test Case | Steps | Expected Result | Priority | Status | Tester | Date | Notes
Authentication
AUTH-001 | Valid Login | 1. Navigate to login page 2. Enter manager@demo.com 3. Enter Password123! 4. Click Login | User redirected to Dashboard | C
AUTH-002 | Invalid Password | 1. Navigate to login page 2. Enter manager@demo.com 3. Enter wrong password 4. Click Login | Error message displayed | C
AUTH-003 | Invalid Email | 1. Navigate to login page 2. Enter nonexistent@demo.com 3. Enter any password | Error message displayed | C
AUTH-004 | Empty Fields | 1. Navigate to login page 2. Leave fields empty 3. Click Login | Validation error shown | H
AUTH-005 | Logout | 1. Login successfully 2. Click Logout button | User redirected to login page | C
AUTH-006 | Session Persistence | 1. Login successfully 2. Close browser tab 3. Reopen application | User remains logged in | H
AUTH-007 | Role-Based Redirect | 1. Login as user@demo.com 2. Observe landing page | User directed to appropriate dashboard | H
Dashboard
DASH-001 | Dashboard Load | 1. Login as manager 2. Navigate to Dashboard | Dashboard displays with all sections loading | C
DASH-002 | KPI Display | 1. View Dashboard 2. Check KPI cards | Total Assets, Total Value, Accumulated Depreciation, NBV displayed correctly | C
DASH-003 | Status Pie Chart | 1. View Dashboard 2. Check Status chart | Pie chart shows assets by status | H
DASH-004 | Value Bar Chart | 1. View Dashboard 2. Check Value by Category chart | Bar chart displays asset values by category | H
DASH-005 | Depreciation Trend | 1. View Dashboard 2. Check trend chart | Line chart shows depreciation trends | H
DASH-006 | Recent Assets | 1. View Dashboard 2. Check Recently Added section | List of recent assets displayed | M
DASH-007 | Filter by Date Range | 1. Select From/To dates 2. Apply filter | Dashboard data filtered to selected period | H
DASH-008 | Filter by Location | 1. Select location filter 2. Apply | Dashboard shows data for selected location | M
DASH-009 | Filter by Category | 1. Select category filter 2. Apply | Dashboard shows data for selected category | M
DASH-010 | Export Summary | 1. Click Export button 2. Select CSV format | CSV file downloads with dashboard data | H
DASH-011 | Export to Excel | 1. Click Export 2. Select Excel format | Excel file downloads correctly | H
DASH-012 | Export to PDF | 1. Click Export 2. Select PDF format | PDF report generates correctly | H
Asset Management
ASSET-001 | Asset List Display | 1. Navigate to Assets 2. View asset list | Paginated list of assets displayed | C
ASSET-002 | Create New Asset | 1. Click Add Asset 2. Fill required fields 3. Save | Asset created successfully | C
ASSET-003 | View Asset Details | 1. Click on asset in list 2. View detail page | All asset information displayed | C
ASSET-004 | Edit Asset | 1. Open asset details 2. Click Edit 3. Modify fields 4. Save | Changes saved and reflected | C
ASSET-005 | Delete Asset | 1. Login as Admin 2. Select asset 3. Click Delete 4. Confirm | Asset removed from list | C
ASSET-006 | Search by Name | 1. Enter asset name in search 2. Press Enter | Matching assets displayed | H
ASSET-007 | Search by Asset Number | 1. Enter asset number in search 2. Press Enter | Matching asset displayed | H
ASSET-008 | Filter by Status | 1. Select status filter (Active) 2. Apply | Only active assets shown | H
ASSET-009 | Filter by Category | 1. Select category filter 2. Apply | Only assets in selected category shown | H
ASSET-010 | Filter by Location | 1. Select location filter 2. Apply | Only assets at selected location shown | H
ASSET-011 | Filter by Condition | 1. Select condition filter 2. Apply | Only assets with selected condition shown | M
ASSET-012 | Column Visibility | 1. Click column settings 2. Hide/show columns | Selected columns visible/hidden | M
ASSET-013 | Sort by Column | 1. Click column header 2. Observe sorting | Data sorted ascending/descending | M
ASSET-014 | Pagination | 1. Navigate through pages 2. Change page size | Correct items per page | M
ASSET-015 | Upload Image | 1. Open asset details 2. Upload image file 3. Save | Image attached to asset | H
ASSET-016 | QR Code Display | 1. Open asset details 2. View QR code section | QR code generated and displayed | H
ASSET-017 | Audit Trail | 1. Open asset details 2. View Audit Trail tab | History of changes displayed | H
ASSET-018 | Export Assets | 1. Click Export button 2. Select format | Asset list exports correctly | H
ASSET-019 | Required Field Validation | 1. Try to create asset 2. Leave required fields empty | Validation errors shown | C
ASSET-020 | Duplicate Asset Number | 1. Create asset with existing number | Error: Asset number already exists | H
Asset Status
STATUS-001 | Change to In Storage | 1. Select active asset 2. Change status to In Storage 3. Confirm | Status changed, depreciation CONTINUES (IAS 16) | C
STATUS-002 | Change to In Maintenance | 1. Select active asset 2. Change status to In Maintenance 3. Confirm | Status changed, depreciation CONTINUES (IAS 16) | C
STATUS-003 | Change to Disposed | 1. Select active asset 2. Change status to Disposed 3. Select effective date 4. Confirm | Status changed, depreciation STOPS (derecognition) | C
STATUS-004 | Status Change Modal | 1. Initiate status change 2. View confirmation modal | Modal shows depreciation impact message | C
STATUS-005 | Effective Date Selection | 1. Initiate disposal 2. Select effective date | Effective date recorded correctly | H
STATUS-006 | Status Change Audit | 1. Change asset status 2. View audit trail | Status change logged with date, user, old/new values | H
Depreciation
DEP-001 | Depreciation Review Page | 1. Navigate to Depreciation Review 2. View page | Depreciation summary and asset list displayed | C
DEP-002 | Preview Depreciation | 1. Select period (From/To) 2. Click Preview | Depreciation calculations shown without saving | C
DEP-003 | Straight Line Method | 1. View asset with SL method 2. Check calculation | Depreciation = (Cost - Residual) / Useful Life | C
DEP-004 | Declining Balance Method | 1. View asset with DB method 2. Check calculation | Depreciation = NBV x Rate | C
DEP-005 | Process Depreciation | 1. Preview depreciation 2. Click Process 3. Confirm | Depreciation recorded, period locked | C
DEP-006 | Period Locking | 1. Process depreciation 2. Try to re-process same period | Error: Period already locked | C
DEP-007 | Sequential Period Validation | 1. Try to process future period 2. Skip current period | Error: Must process periods sequentially | C
DEP-008 | View Depreciation Schedule | 1. Select asset 2. View depreciation schedule | Year-by-year depreciation shown | H
DEP-009 | Depreciation by Category | 1. View breakdown by category | Totals by category displayed correctly | H
DEP-010 | Depreciation by Location | 1. View breakdown by location | Totals by location displayed correctly | H
DEP-011 | Edit Before Processing | 1. Preview depreciation 2. Edit asset parameters 3. Preview again | Updated calculations reflected | H
DEP-012 | NBV Calculation | 1. View asset depreciation 2. Verify NBV | NBV = Cost - Accumulated Depreciation | C
DEP-013 | Zero Depreciation at End | 1. View fully depreciated asset | Depreciation stops at residual value | C
Wear & Tear (Tax)
WT-001 | W&T Register Display | 1. Navigate to Wear & Tear Register 2. View register | List of assets with tax depreciation info | C
WT-002 | SARS Section Display | 1. View W&T register 2. Check SARS section column | Each asset shows mapped SARS section | C
WT-003 | Tax Rate Calculation | 1. View asset W&T 2. Verify tax depreciation | W&T calculated using SARS rates | C
WT-004 | Preview W&T Processing | 1. Select tax year 2. Click Preview | W&T calculations shown without committing | C
WT-005 | Process W&T | 1. Preview W&T 2. Click Process 3. Confirm | W&T recorded, period locked | C
WT-006 | Export W&T Register | 1. Click Export 2. Select CSV | W&T register exports for tax filing | H
WT-007 | W&T by SARS Section | 1. View breakdown by SARS section | Assets grouped by Section 11/12 | H
WT-008 | Tax Book Value (TBV) | 1. View asset W&T details 2. Verify TBV | TBV = Cost - Accumulated Tax Depreciation | C
WT-009 | Category Tax Mapping | 1. Go to Settings > Tax 2. Map category to SARS section | Mapping saved, applied to assets | H
WT-010 | Tax Useful Life | 1. View asset W&T 2. Check useful life | Tax useful life matches SARS schedule | H
Reporting
RPT-001 | Access Reports Page | 1. Navigate to Reports 2. View available reports | Report selection page displayed | H
RPT-002 | Asset Inventory Report | 1. Select Inventory Report 2. Apply filters 3. Generate | Complete asset listing displayed | C
RPT-003 | Depreciation Report | 1. Select Depreciation Report 2. Select period 3. Generate | Depreciation details for period shown | C
RPT-004 | Value Summary Report | 1. Select Value Summary 2. Group by category 3. Generate | Asset values grouped correctly | H
RPT-005 | Condition Report | 1. Select Condition Report 2. Generate | Assets listed by condition status | H
RPT-006 | Custodian Report | 1. Select Custodian Report 2. Generate | Assets grouped by custodian | H
RPT-007 | Audit Trail Report | 1. Select Audit Report 2. Select date range 3. Generate | All changes in period listed | H
RPT-008 | Export to CSV | 1. Generate any report 2. Export as CSV | CSV file downloads correctly | H
RPT-009 | Export to Excel | 1. Generate report 2. Export as Excel | Excel file with formatting downloads | H
RPT-010 | Export to PDF | 1. Generate report 2. Export as PDF | PDF report generates correctly | H
RPT-011 | Report Filtering | 1. Generate report 2. Apply multiple filters | Filtered data displayed correctly | M
RPT-012 | Report Data Accuracy | 1. Generate report 2. Verify against source data | Report totals match source data | C
User Management
USER-001 | View Users | 1. Login as Admin 2. Navigate to Settings > Users | List of tenant users displayed | H
USER-002 | Create User | 1. Click Add User 2. Enter email, name, role 3. Set password 4. Save | User created, can login | C
USER-003 | Edit User | 1. Select user 2. Edit details 3. Save | User information updated | H
USER-004 | Deactivate User | 1. Select user 2. Click Deactivate | User cannot login | C
USER-005 | Reset Password | 1. Select user 2. Click Reset Password 3. Set new password | User can login with new password | C
USER-006 | Role Assignment | 1. Edit user 2. Change role 3. Save 4. User logs in | User has new role permissions | C
USER-007 | Duplicate Email | 1. Create user with existing email | Error: Email already exists | H
USER-008 | User Access Control | 1. Login as User role 2. Try to access Admin features | Access denied / features hidden | C
Security
SEC-001 | Protected Routes | 1. Logout 2. Try to access /dashboard directly | Redirected to login page | C
SEC-002 | Manager Restrictions | 1. Login as Manager 2. Try to delete asset | Delete option not available | C
SEC-003 | User Restrictions | 1. Login as User 2. Try to access Settings > Users | Access denied / not visible | C
SEC-004 | Tenant Isolation | 1. Login as tenant A user 2. View assets | Only tenant A assets visible | C
SEC-005 | Session Timeout | 1. Login 2. Wait for session timeout 3. Try to access page | Redirected to login | H
SEC-006 | Token Expiry | 1. Login 2. Wait for token expiry 3. Make API request | Unauthorized error, redirect to login | H

## Summary
Module | Total Tests | Passed | Failed | N/A | Pass Rate
Authentication | 7
Dashboard | 12
Asset Management | 20
Asset Status | 6
Depreciation | 13
Wear & Tear (Tax) | 10
Reporting | 12
User Management | 8
Security | 6
TOTAL | 94

## Sign-Off
PKF ASSET MANAGEMENT SYSTEM
USER ACCEPTANCE TESTING SIGN-OFF
UAT Start Date:
UAT End Date:
System Accepted: | Yes / No / Conditional
Conditions (if any):
APPROVALS
Role | Name | Title | Signature | Date
Client Representative
Business Owner
IT Representative
Project Manager